## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | As a user, I want to upload PDF, DOCX, PPTX & TXT documents | MUST HAVE | None | Shaheen Begum | 3- Completed
Sprint 2 | Sprint 2 | US-02 | As a user, I want semantic search using vector embeddings | MUST HAVE | US-01 | Shaheen Begum | 3- Completed
Sprint 3 | Sprint 3 | US-03 | As a user, I want conversational Q&A with corrective RAG | MUST HAVE | US-02 | Shaheen Begum | 3- Completed
Sprint 4 | Sprint 4 | US-04 | As a user, I want source citations in every answer | SHOULD HAVE | US-03 | Shaheen Begum | 3- Completed
Sprint 5 | Sprint 5 | US-05 | As a user, I want follow-up question handling & conversation history | SHOULD HAVE | US-04 | Shaheen Begum | 3- Completed
Sprint 6 | Sprint 6 | US-06 | As a user, I want modern attractive UI with consistent footer | COULD HAVE | US-03 | Shaheen Begum | 3- Completed
Sprint 7 | Sprint 7 | US-07 | As a user, I want clear error messages for invalid files | COULD HAVE | US-01 | Shaheen Begum | 3- Completed
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 15 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-03 | T-01 | As a user, I want clear error messages for invalid files | 2026-03-03 | 2026-03-05 | Asraf A | Coding | 3- Completed | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T-02 | Integrate Groq LLM (Llama & Qwen models) | 2026-03-06 | 2026-03-08 | Asraf A | Integration Test | 3- Completed | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T-03 | Add conversation history handling | 2026-03-10 | 2026-03-12 | Asraf A | Coding | 3- Completed | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T-04 | Add source citation logic in answers | 2026-03-13 | 2026-03-15 | Asraf A | Design | 3- Completed | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T-05 | Implement model switching feature | 2026-03-17 | 2026-03-20 | Asraf A | Unit Test | 3- Completed |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | None | Started document ingestion setup and environment configuration
Sprint 2 | Day 2 | Embedding generation quota issues | Referred official LangChain documentation and resolved configuration
Sprint 3 | Day 3 | Groq API key not loading in backend | Tested multiple chunk sizes and finalized optimal configuration
Sprint 4 | Day 4 | UI changes not reflecting | Switched to Hugging Face sentence-transformer model to resolve embedding generation
Sprint 4 | Day 5 | Large PDF files processing slowly | Optimized retrieval logic and vector search parameters
Sprint 5 | Day 6 | Model selector not updating | Fixed state binding in ChatState
Sprint 5 | Day 7 | Empty query causing error | Added input validation
Sprint 6 | Day 8 | Follow-up questions losing context | Improved history handling
Sprint 6 | Day 9 | None | Continued UI improvements
Sprint 7 | Day 10 | None | Final testing completed

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 2026-03-02 | 2026-03-07 | Shaheen Begum | Better Planning | Last-minute coding | Regular testing | Follow sprint plan
2 | 2 | 2026-03-08 | 2026-03-12 | Shaheen Begum | Free Embedding | Paid APIs | Clean code | switched to HuggingFace
3 | 3 | 2026-03-14 | 2026-03-18 | Shaheen Begum | Corrective RAG | Ignoring API issues | Daily testing | Fixed Groq key
4 | 4 | 2026-03-21 | 2026-03-23 | Shaheen Begum | Modern UI | Old design | Clean rebuild | Updated all pages
5 | 5 | 2026-03-24 | 2026-03-25 | Shaheen Begum | Test cases | Manual testing | Code comments | Created Unit Test Plan
6 | 6 | 2026-03-26 | 2026-03-31 | Shaheen Begum | Source citations | Forgetting sources | code review | Added sources in answers
7 | 7 | 2026-04-01 | 2026-04-02 | Shaheen Begum | Quick bug fixing | Delaying fixes | Daily meetings | Project completed successfully